## MF-DM&Timeline
Legend = {WF: Wireframe, B: Build, UI: User Interface Feature, DM: Data Modeling} | [7 empty] | 2015-03-13 | Project Timeline
Today is | 2015-03-13 | now, go get shit done. | [6 empty] | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Deliverable | Data Modeling | Route/NG | Controller | Services | Mobile Breakpoint | Other Breakpoints | UI Comments | User Story | 2015-03-06 | 2015-03-07 | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-03-14 | 2015-03-15 | 2015-03-16 | 2015-03-17 | 2015-03-18 | 2015-03-19 | 2015-03-20 | 2015-03-21 | 2015-03-22 | 2015-03-23 | 2015-03-24 | 2015-03-25 | 2015-03-26 | 2015-03-27
Github Repo |  | Allow Users, Collaborators & Potential Employers to understand the MF project. | [6 empty] | Completed
- README.md |  | Comment: Allow Users, Collaborators & Potential Employers to understand the MF project. | [6 empty] | Completed/Continually Updating
- WireFrame:
WF_Welcome_Page | [8 empty] | Completed
B_Welcome_Page |  | '/welcome' |  |  |  |  | Main App Route
UI_Login/RegisterPage_Link | ui-sref="login" | '/login' |  |  | Visible, top right | Visible, top right | Route on click to Login/Register Page
UI_Estimate_INPUT | 'integer', 2 decimals | Visible |  |  |  |  | Feed Estimate Input Model to Analysis Controller for Calculations
UI_EstimateButton_BTN | ui-sref="analysis" | '/analysis'
WF_WelcomeAnalysis_Page | [8 empty] | Completed
B_WelcomeAnalysis_Page |  | '/analysis'
UI_AgeSelector_Selector | select: integer (0-100), no decimals | NA |  |  |  |  | Apple scroll selector. | Only show selected year for comparison.
UI_Stocks_Table | <table> | Visible | StocksCtrl |  | selector view | table view to fit | Header until click, then show # of th's & td's depending on breakpoint | 1 Yr v. increment 5
UI_Stocks_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_StockYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_StockBOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_StockGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_StockTaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_StockEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsAcct_Table | <table> | Visible | SavingsAccountCtrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsAcct_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_SavingsYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsBOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsTaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_SavingsEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)_Table | <table> | Visible | 401Ctrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_401(k)Year_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)BOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)Gain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)Taxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_401(k)EOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)_Table | <table> | Visible | Roth401Ctrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_Roth401(k)Year_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)BOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)Gain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)Taxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_Roth401(k)EOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRA_Table | <table> | Visible | IRACtrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRA_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_IRAYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRABOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRAGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRATaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IRAEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRA_Table | <table> | Visible | RothIRACtrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRA_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_RothIRAYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRABOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRAGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRATaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RothIRAEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL_Table | <table> | Visible | ULCtrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL_Modal | 'string' | <ng-show> |  |  |  |  | on click, reveal $ storage info | user wants info
UI_ULYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_ULBOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_ULGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_ULTaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_ULEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&Trust_Table | <table> | Visible | UL&TrustCtrl |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&Trust_Modal | 'string' | <ng-show> |  |  | <ng-click> |  | on click, reveal $ storage info | user wants info
UI_UL&TrustYear_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&TrustBOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&TrustGain/Loss_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&TrustTaxes_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_UL&TrustEOY_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_ActButton_BTN | ui-sref="login" | Visible |  |  |  |  | mobile=selector view, lg=incremented view | user wants annual view
WF_Login/Register_Page | [8 empty] | Completed
B_Login/Register_Page
UI_Email_INPUT | 'email' | Always Visible |  |  |  |  | Visible for login & register
UI_Password_INPUT | 'password' | Always Visible |  |  |  |  | Visible for login & register
UI_LoginButton_BTN | POST to DB | ui-sref="dashboard"'<ng-show="register"> |  |  |  |  | Hide on register click
UI_RegisterButton_BTN | <ng-show="register"> | Always Visible |  |  |  |  | Hide on click
UI_FirstName_INPUT | 'string' | Always Visible
UI_LastName_INPUT | 'string' | Always Visible
UI_DOB_INPUT | 'date' | <ng-show="register">
UI_ConfirmPassword_INPUT | 'password' | <ng-show="register">
UI_RegisterSubmitButton_BTN | POST to DB | ui-sref="info"
PROJECT MUST BE BRANCHED AT THIS POINT FOR FUTURE DEVELOPMENT IF CANNOT BE COMPLETED BY DEMO DAY | [8 empty] | PROJECT MUST BE BRANCHED AT THIS POINT FOR FUTURE DEVELOPMENT IF CANNOT BE COMPLETED BY DEMO DAY
WF_UserData_Page | [9 empty] | Completed
B_UserData_Page
Storage
UI_IncomeStorage_MODAL | 'string' | <ng-show>, Kindo-window |  |  | <ng-click> |  | on click, reveal $ storage info | user wants info
UI_IncomeStorage_Table | <table> | Visible |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IncomeStorageName_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_BalanceUpdate_INPUT_TD | POST to DB | <ng-repeat>
UI_RemoveButton_BTN_TD | DELETE from DB
UI_StorageName_INPUT
UI_StorageBalance_INPUT
UI_StorageAddButton_BTN | POST to DB
Income
UI_Income_MODAL | 'string' | <ng-show>, Kindo-window |  |  | <ng-click> |  | on click, reveal $ storage info | user wants info
UI_Income_Table | <table> | Visible |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IncomeName_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_IncomeFrequency_TD |  | <ng-repeat>
UI_IncomeDayOrDate_TD |  | <ng-repeat>
UI_IncomeAmount_TD |  | <ng-repeat>
UI_IncomeStorageLocation_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RemoveButton_BTN_TD | DELETE from DB
UI_IncomeName_INPUT
UI_IncomeFrequencySchedule_SELECTOR | PaySchedule = ['Hourly', 'Weekly', '1st & 15th', 'Every other Friday', 'Monthly']
UI_ScheduleIncomeHours_INPUT | integer, between 0 -168. +2 decimals | <ng-show="hourlyInput"> |  |  |  |  | Will be hidden unless the "houly" schedule is chosen | Allow for part-time or hourly workers
UI_ScheduleIncomeDay_SELECTOR | weekDays = ['Monday', 'Tuesday', 'Wednesday', 'Thursday', 'Friday', 'Saturday', 'Sunday'] | <ng-show="weeklySelector"> |  |  |  |  | Will be hidden unless the "weekly" selector is chose
UI_IncomeAmount_INPUT | integer, > 0, +2 decimals | [6 empty] | What's your income for the above time period?
UI_TaxStatus_SELECTOR | taxes = ['before taxes', 'after taxes']
UI_StorageLocation_SELECTOR
UI_IncomeAddButton_BTN
Outcome
UI_Outcome_MODAL | 'string' | <ng-show>, Kindo-window |  |  | <ng-click> |  | on click, reveal $ storage info | user wants info
UI_Outcome_Table | <table> | Visible |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_OutcomeName_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_OutcomeFrequency_TD |  | <ng-repeat>
UI_OutcomeDayOrDate_TD |  | <ng-repeat>
UI_OutcomeAmount_TD |  | <ng-repeat>
UI_OutcomeLocation_TD | <td within th & tr> | <ng-repeat> |  |  | selector view | table view to fit | mobile=selector view, lg=incremented view | user wants annual view
UI_RemoveButton_BTN_TD | DELETE from DB
UI_OutcomeName_INPUT
UI_OutcomeFrequencySchedule_SELECTOR | PaySchedule = ['Hourly', 'Weekly', '1st & 15th', 'Every other Friday', 'Monthly']
UI_ScheduleIncomeDay_SELECTOR | weekDays = ['Monday', 'Tuesday', 'Wednesday', 'Thursday', 'Friday', 'Saturday', 'Sunday'] | <ng-show="weeklySelector"> |  |  |  |  | Will be hidden unless the "weekly" selector is chose
UI_ScheduleIncomeDate_SELECTOR | weekDays = ['Monday', 'Tuesday', 'Wednesday', 'Thursday', 'Friday', 'Saturday', 'Sunday'] | <ng-show="weeklySelector"> |  |  |  |  | Will be hidden unless the "weekly" selector is chose
UI_OutcomeAmount_INPUT | integer, > 0, +2 decimals | [6 empty] | What's your income for the above time period?
UI_OutcomeLocation_SELECTOR
UI_OutcomeAddButton_BTN
WF_UserDashboard_NAV
B_UserDashboard_NAV
UI/DM_DailyView
WF_UserDaily
B_UserDaily
WF_UserWeekly
B_UserWeekly
WF_UserMonthly
B_UserMonthly
WF_UserAnnually
B_UserAnnually

## FinanceDataModeling (hidden)
millennialfalcon.co/finance
Goals:
Automating Lifetime Financial Planning
Views | Daily View | Weekly View | Monthly View | Annual View | Lifetime View | Generational View
Income
Is it payday? Starting and Ending Account Balance
Bills | Bills Due Today
Outcome
Income
Where does your currency come from? Do you pay your income taxes every paycheck or does your employer?
Tax-Situation | Self-employed | Contract | Salary
Outcome
Automate Lifetime Bill & Debt Planning
Category | Needs | Other
| Housing | Food
| Nutriton | Travel
| Energy | Experiences
| Education | Credit
| Transportation | Auto Loan
| Healthcare | Student Loan
Storage
Goal | Daily Use | Emergency Fund | Education | Self-Sustainabilty | Retirement | Generational
Storage Medium | Cash | Savings Acct.
| Checking Acct. | 401(k)
Roth 401(k)
IRA
Roth IRA

## WF_M_LandingPage (hidden)
millennialfalcon.co/finance/#/welcome
Landing Page
Mobile
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar
|  | LogIn/Register | <ng-show>: "Login/Register" or "Logoff"
| We Make "Finances" Understandable. |  | <ng-href="login">
Millennial Falcon assists humans in understanding, estimating, and automating their entire financial lives.
Give it a Try:
| Number of $$ you could put away each month. | Estimate

## WF_D_Welcome
Welcome
Tablet/Desktop
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar
|  |  | LogIn/Register | <ng-show>: "Login/Register" or "Logoff"
We Make "Finances" Understandable. |  |  |  | <ng-href="login">
The mission of Millennial Falcon is to assist humans in understanding and estimating our entire financial lives. From debt, income, and goal mapping to connecting with someone who can help you automate your interaction with finance and plan for the future.
| Number of $$ you could put away each month. | Estimate
*Smoked Image as background

## WF_D_UserData_Page
User Data Page
[11 empty] | Before Taxes | Monday | Daily | Hourly
[11 empty] | After Taxes | Tuesday | Weekly | Weekly
Tablet/Desktop | [11 empty] | Wednesday | Bi-weekly | 1st & 15th
URL: https://www.millennialfalcon.co | [11 empty] | Thursday | Monthly | Every other Week
toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar | [12 empty] | Annually | Monthly
Satuday
We Make "Finances" Understandable. | [11 empty] | Sunday
1. Add Your Income Storage Info
| This modal will explain the Storage section | [8 empty] | Modal, will show"More Info" until clicked
Current Income Storage Locations
|  | Income Storage |  | Balance |  |  |  | Remove
|  | Checking |  | 1100
|  | Savings |  | 5000
Add Storage Location
|  | Storage Name |  | Hugh's Roth 401k
|  | Balance |  | 6000
Add
2. Add Your Income Info
| This modal will explain the income section | [8 empty] | Modal, will show"More Info" until clicked
Current Incomes
|  | Income |  | Frequency | Pay Day or Date | Amount | Storage Location | Remove
|  | Hugh's Salary |  | 1st & 15th | 1, 15 | 3000 | Checking
Add an Income
|  | Income Name |  | Karissa's Salary
|  | Income Schedule |  | Weekly
|  | Average Hours Per Week |  | 0 | [5 empty] | ng-show if "weekly" is selected
|  | Weekly Pay Day |  | Monday
|  | Income Amount |  | 3000
|  | Income Taxes |  | After Taxes
|  | Storage Location |  | Checking | [5 empty] | Let user choose from current locations, otherwise force them to add locations to add incomes
Add
3. Add Your Outcome Info
Friday
| This modal will explain the outcome section | [8 empty] | Modal, will show"More Info" until clicked
Current Outcomes
|  | Outcome |  | Frequency | Due Day or Date | Amount | Outcome Location | Remove
|  | Apartment Rent |  | Monthly | 1 | 1000 | Checking
Add an Outcome
|  | Outcome Name |  | Netflix
|  | Outcome Frequency |  | Monthly
|  | Weekly Due Day |  | Monday | [5 empty] | <ng-show> if "weekly" frequency is selected
|  | Monthly Due Date |  | 1 | [5 empty] | <ng-show> if "monthly" frequency is selected
|  | Amount due |  | 8
|  | Outcome Location |  | Checking
Add
Angular Widgets
|  |  | Thanks, that's all we needed! | [5 empty] | Submit

## WF_M_LandingAnalysisPage (hidden)
millennialfalcon.co/finance/#/welcome
Landing Page
Mobile
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar
|  |  |  | LogIn/Register |  | <ng-show>: "Login/Register" or "Logoff"
| Iphone style year selector (Integer 1-100) |  |  |  |  | <ng-href="login">
How would like to see the data?
| Table |  |  | Graph
Stocks
| Info Modal explaining how info was calculated and the tax effects on this storage medium. | [5 empty] | UI_StockYear_TD
| Year | Start of Year | Gain / Loss | Taxes | End of Year |  | UI_StockBOY_TD
| 10 | 7000 | 350 | 70 | 7280 |  | UI_StockGain/Loss_TD | 350 | 70
UI_StockTaxes_TD
| Savings Account | [5 empty] | UI_StockEOY_TD
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
401(k)
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Roth 401(k)
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
IRA
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Roth IRA
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Universal Life Insurance
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Universal Life Insurance & Dynasty Trust
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
*Circular 230 disclaimer.
*IRS Circular 230 Information: To ensure compliance with requirements imposed by the IRS, we inform you that any tax advice contained in this communication (including any attachments) was not intended or written to be used, and cannot be used, for the purpose of (i) avoiding penalties under the Internal Revenue Code or (ii) promoting, marketing or recommending to another party any transaction or matter addressed herein.

## WF_M_Login-Register_Page (hidden)
millennialfalcon.co/finance/#/welcome
Landing Page
Mobile
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar
|  | LogIn/Register | <ng-show>: "Login/Register" or "Logoff"
| We Make "Finances" Understandable. |  | <ng-href="login">
Millennial Falcon assists humans in understanding, estimating, and automating their entire financial lives.
Give it a Try:
| Number of $$ you could put away each month. | Estimate

## WF_D_Login-Register_Page
Login/Register Page
Tablet/Desktop
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar_toolbar
We Make "Finances" Understandable.
| Login |  |  | This section will be visible when routed to and hide when the register button is clicked.
| Your Email | Email
| Your Password | Password
Login
| Don’t' have a falcon yet?? |  | Register
| Register |  |  | This section will be hidden until the register button is clicked.
| First Name | First Name
| Last Name | Last Name
| Date of Birth | MM/DD/YYYY
| Password | Password
| Confirm Password | Confirm Password
| Now, let's get your falcon soaring.. |  | Register

## WF_M_UserInfo_Page (hidden)
millennialfalcon.co/finance/#/welcome
Landing Page
Mobile
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar
|  | LogIn/Register | <ng-show>: "Login/Register" or "Logoff"
| We Make "Finances" Understandable. |  | <ng-href="login">
Millennial Falcon assists humans in understanding, estimating, and automating their entire financial lives.
Give it a Try:
| Number of $$ you could put away each month. | Estimate

## WF_D_WelcomeAnalysis
millennialfalcon.co/finance/#/welcome
Welcome Analysis Page
Mobile
URL: https://www.millennialfalcon.co
toolbar_toolbar_toolbar_toolbar
|  |  |  | LogIn/Register |  | <ng-show>: "Login/Register" or "Logoff"
|  | What year would you like to analyze? |  |  |  | <ng-href="login">
10
Now, how would like to see the Analysis?
|  | Table |  | Graph
Stocks
| Info Modal explaining how info was calculated and the tax effects on this storage medium. | [5 empty] | UI_StockYear_TD
| Year | Start of Year | Gain / Loss | Taxes | End of Year |  | UI_StockBOY_TD
| 10 | 7000 | 350 | 70 | 7280 |  | UI_StockGain/Loss_TD | 350 | 70
UI_StockTaxes_TD
| Savings Account | [5 empty] | UI_StockEOY_TD
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
401(k)
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Roth 401(k)
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
IRA
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Roth IRA
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Universal Life Insurance
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
Universal Life Insurance & Dynasty Trust
Info Modal explaining how info was calculated and the tax effects on this storage medium.
| Year | Start of Year | Gain / Loss | Taxes | End of Year
| 10 | 7000 | 350 | 70 | 7280
*Circular 230 disclaimer.
*IRS Circular 230 Information: To ensure compliance with requirements imposed by the IRS, we inform you that any tax advice contained in this communication (including any attachments) was not intended or written to be used, and cannot be used, for the purpose of (i) avoiding penalties under the Internal Revenue Code or (ii) promoting, marketing or recommending to another party any transaction or matter addressed herein.

## DataModeling
Data Models
| Storage |  |  |  | UserProfile |  |  |  |  | Income |  |  |  |  | Outcome
| Attribute | Type | Required | Model | attribute | type | required | Model | via | attribute | type | required | Model | via | attribute | type | required | Model | via
| user |  |  | UserProfile | user |  |  | User |  | user |  |  | UserProfile |  | user |  |  | UserProfile
| name | string | TRUE |  | storage |  |  | storage | user | name | string | TRUE |  |  | name | string | TRUE
| balance | integer | TRUE |  | income |  |  | income | user | frequency | string | TRUE |  |  | frequency | string | TRUE
[5 empty] | outcome |  |  | outcome | user | hours | integer | FALSE |  |  | dueDay | string | FALSE
[5 empty] | firstName | string | TRUE |  |  | weekday | string | FALSE |  |  | dueDate | integer | FALSE
[5 empty] | lastName | string | TRUE |  |  | amount | integer | TRUE |  |  | amount | integer | TRUE
[5 empty] | dateOfBirth | date | TRUE |  |  | taxes | string | TRUE |  |  | location: | string | TRUE
[5 empty] | email | string | TRUE |  |  | location | string | TRUE
[5 empty] | password | string | TRUE

## Sheet1
| 0.055 |  |  | 0.25 | 0.15
1 | 5000 | 275 | 5275 | 68.75 | 41.25
2 | 5275 | 290.125 | 5565.125 | 72.5312 | 43.5187
3 | 5565.125 | 306.0819 | 5871.2069 | 76.5205 | 45.9123
4 | 5871.2069 | 322.9164 | 6194.1233 | 80.7291 | 48.4375
5 | 6194.1233 | 340.6768 | 6534.8 | 85.1692 | 51.1015
6 | 6534.8 | 359.414 | 6894.214 | 89.8535 | 53.9121
7 | 6894.214 | 379.1818 | 7273.3958 | 94.7954 | 56.8773
8 | 7273.3958 | 400.0368 | 7673.4326 | 100.0092 | 60.0055
9 | 7673.4326 | 422.0388 | 8095.4714 | 105.5097 | 63.3058
10 | 8095.4714 | 445.2509 | 8540.7223 | 111.3127 | 66.7876
11 | 8540.7223 | 469.7397 | 9010.462 | 117.4349 | 70.461
12 | 9010.462 | 495.5754 | 9506.0374 | 123.8939 | 74.3363
13 | 9506.0374 | 522.8321 | 10028.8695 | 130.708 | 78.4248
14 | 10028.8695 | 551.5878 | 10580.4573 | 137.897 | 82.7382
15 | 10580.4573 | 581.9252 | 11162.3825 | 145.4813 | 87.2888
16 | 11162.3825 | 613.931 | 11776.3135 | 153.4828 | 92.0897
17 | 11776.3135 | 647.6972 | 12424.0107 | 161.9243 | 97.1546
18 | 12424.0107 | 683.3206 | 13107.3313 | 170.8301 | 102.4981
19 | 13107.3313 | 720.9032 | 13828.2346 | 180.2258 | 108.1355
20 | 13828.2346 | 760.5529 | 14588.7875 | 190.1382 | 114.0829
21 | 14588.7875 | 802.3833 | 15391.1708 | 200.5958 | 120.3575
22 | 15391.1708 | 846.5144 | 16237.6852 | 211.6286 | 126.9772
23 | 16237.6852 | 893.0727 | 17130.7578 | 223.2682 | 133.9609
24 | 17130.7578 | 942.1917 | 18072.9495 | 235.5479 | 141.3288
25 | 18072.9495 | 994.0122 | 19066.9617 | 248.5031 | 149.1018
26 | 19066.9617 | 1048.6829 | 20115.6446 | 262.1707 | 157.3024
27 | 20115.6446 | 1106.3605 | 21222.0051 | 276.5901 | 165.9541
28 | 21222.0051 | 1167.2103 | 22389.2154 | 291.8026 | 175.0815
29 | 22389.2154 | 1231.4068 | 23620.6222 | 307.8517 | 184.711
30 | 23620.6222 | 1299.1342 | 24919.7564 | 324.7836 | 194.8701
31 | 24919.7564 | 1370.5866 | 26290.343 | 342.6467 | 205.588
32 | 26290.343 | 1445.9689 | 27736.3119 | 361.4922 | 216.8953
33 | 27736.3119 | 1525.4972 | 29261.8091 | 381.3743 | 228.8246
34 | 29261.8091 | 1609.3995 | 30871.2086 | 402.3499 | 241.4099
35 | 30871.2086 | 1697.9165 | 32569.125 | 424.4791 | 254.6875
36 | 32569.125 | 1791.3019 | 34360.4269 | 447.8255 | 268.6953
37 | 34360.4269 | 1889.8235 | 36250.2504 | 472.4559 | 283.4735
38 | 36250.2504 | 1993.7638 | 38244.0142 | 498.4409 | 299.0646
39 | 38244.0142 | 2103.4208 | 40347.4349 | 525.8552 | 315.5131
40 | 40347.4349 | 2219.1089 | 42566.5439 | 554.7772 | 332.8663
41 | 42566.5439 | 2341.1599 | 44907.7038 | 585.29 | 351.174
42 | 44907.7038 | 2469.9237 | 47377.6275 | 617.4809 | 370.4886
43 | 47377.6275 | 2605.7695 | 49983.397 | 651.4424 | 390.8654
44 | 49983.397 | 2749.0868 | 52732.4838 | 687.2717 | 412.363
45 | 52732.4838 | 2900.2866 | 55632.7704 | 725.0717 | 435.043
46 | 55632.7704 | 3059.8024 | 58692.5728 | 764.9506 | 458.9704
47 | 58692.5728 | 3228.0915 | 61920.6643 | 807.0229 | 484.2137
48 | 61920.6643 | 3405.6365 | 65326.3009 | 851.4091 | 510.8455
49 | 65326.3009 | 3592.9465 | 68919.2474 | 898.2366 | 538.942
50 | 68919.2474 | 3790.5586 | 72709.806 | 947.6397 | 568.5838
51 | 72709.806 | 3999.0393 | 76708.8454 | 999.7598 | 599.8559
52 | 76708.8454 | 4218.9865 | 80927.8318 | 1054.7466 | 632.848
53 | 80927.8318 | 4451.0308 | 85378.8626 | 1112.7577 | 667.6546
54 | 85378.8626 | 4695.8374 | 90074.7 | 1173.9594 | 704.3756
55 | 90074.7 | 4954.1085 | 95028.8085 | 1238.5271 | 743.1163
56 | 95028.8085 | 5226.5845 | 100255.393 | 1306.6461 | 783.9877
57 | 100255.393 | 5514.0466 | 105769.4396 | 1378.5117 | 827.107
58 | 105769.4396 | 5817.3192 | 111586.7588 | 1454.3298 | 872.5979
59 | 111586.7588 | 6137.2717 | 117724.0305 | 1534.3179 | 920.5908
60 | 117724.0305 | 6474.8217 | 124198.8522 | 1618.7054 | 971.2233
61 | 124198.8522 | 6830.9369 | 131029.7891 | 1707.7342 | 1024.6405
62 | 131029.7891 | 7206.6384 | 138236.4275 | 1801.6596 | 1080.9958
63 | 138236.4275 | 7603.0035 | 145839.431 | 1900.7509 | 1140.4505
64 | 145839.431 | 8021.1687 | 153860.5997 | 2005.2922 | 1203.1753
65 | 153860.5997 | 8462.333 | 162322.9327 | 2115.5832 | 1269.3499
66 | 162322.9327 | 8927.7613 | 171250.694 | 2231.9403 | 1339.1642
67 | 171250.694 | 9418.7882 | 180669.4822 | 2354.697 | 1412.8182
68 | 180669.4822 | 9936.8215 | 190606.3037 | 2484.2054 | 1490.5232
69 | 190606.3037 | 10483.3467 | 201089.6504 | 2620.8367 | 1572.502
70 | 201089.6504 | 11059.9308 | 212149.5812 | 2764.9827 | 1658.9896
71 | 212149.5812 | 11668.227 | 223817.8081 | 2917.0567 | 1750.234
72 | 223817.8081 | 12309.9794 | 236127.7876 | 3077.4949 | 1846.4969
73 | 236127.7876 | 12987.0283 | 249114.8159 | 3246.7571 | 1948.0542
74 | 249114.8159 | 13701.3149 | 262816.1308 | 3425.3287 | 2055.1972
75 | 262816.1308 | 14454.8872 | 277271.018 | 3613.7218 | 2168.2331
76 | 277271.018 | 15249.906 | 292520.9239 | 3812.4765 | 2287.4859
77 | 292520.9239 | 16088.6508 | 308609.5748 | 4022.1627 | 2413.2976
78 | 308609.5748 | 16973.5266 | 325583.1014 | 4243.3817 | 2546.029
79 | 325583.1014 | 17907.0706 | 343490.1719 | 4476.7676 | 2686.0606
80 | 343490.1719 | 18891.9595 | 362382.1314 | 4722.9899 | 2833.7939
81 | 362382.1314 | 19931.0172 | 382313.1486 | 4982.7543 | 2989.6526
82 | 382313.1486 | 21027.2232 | 403340.3718 | 5256.8058 | 3154.0835
83 | 403340.3718 | 22183.7204 | 425524.0923 | 5545.9301 | 3327.5581
84 | 425524.0923 | 23403.8251 | 448927.9173 | 5850.9563 | 3510.5738
85 | 448927.9173 | 24691.0355 | 473618.9528 | 6172.7589 | 3703.6553
86 | 473618.9528 | 26049.0424 | 499667.9952 | 6512.2606 | 3907.3564
87 | 499667.9952 | 27481.7397 | 527149.7349 | 6870.4349 | 4122.261
88 | 527149.7349 | 28993.2354 | 556142.9703 | 7248.3089 | 4348.9853
89 | 556142.9703 | 30587.8634 | 586730.8337 | 7646.9658 | 4588.1795
90 | 586730.8337 | 32270.1959 | 619001.0296 | 8067.549 | 4840.5294
91 | 619001.0296 | 34045.0566 | 653046.0862 | 8511.2642 | 5106.7585
92 | 653046.0862 | 35917.5347 | 688963.6209 | 8979.3837 | 5387.6302
93 | 688963.6209 | 37892.9992 | 726856.6201 | 9473.2498 | 5683.9499
94 | 726856.6201 | 39977.1141 | 766833.7342 | 9994.2785 | 5996.5671
95 | 766833.7342 | 42175.8554 | 809009.5896 | 10543.9638 | 6326.3783
96 | 809009.5896 | 44495.5274 | 853505.117 | 11123.8819 | 6674.3291
97 | 853505.117 | 46942.7814 | 900447.8984 | 11735.6954 | 7041.4172
98 | 900447.8984 | 49524.6344 | 949972.5328 | 12381.1586 | 7428.6952
99 | 949972.5328 | 52248.4893 | 1002221.0222 | 13062.1223 | 7837.2734
100 | 1002221.0222 | 55122.1562 | 1057343.1784 | 13780.5391 | 8268.3234